# PowerPoint Outline: Sales Trends Improvement

Purpose: Summarize the sales trends review, highlight supply chain and regional performance issues, and align leaders on corrective actions for January–February 2025.

## Slide 1 — Title

- Sales Trends Improvement Project

- Supply Chain Challenges, Data Findings, and Recommended Actions

- Project period: January–February 2025

## Slide 2 — Executive Summary

- Running Shoes sales and gross revenue declined for three consecutive months in the Northeast and Midwest.

- Product availability was constrained by backorders and a 12-day warehouse restocking delay linked to vendor inconsistencies.

- Regional analysis points to different root causes: lower foot traffic and higher returns in the Northeast; distribution lag in the Midwest.

- The response combines dual sourcing, regional analysis, an Apparel campaign pilot, improved Electronics promotion timing, and stronger governance.

## Slide 3 — Business Context and Objectives

- Reverse declining Running Shoes performance in priority regions.

- Reduce stock disruption caused by supplier and distribution delays.

- Increase Apparel campaign visibility while improving promotional timing for Electronics.

- Incorporate revised regional, marketing, and supply assumptions into the next forecast.

- Track execution through biweekly reviews and consolidated executive reporting.

## Slide 4 — Supply Chain Challenges

- Running Shoes experienced repeated backorders, reducing product availability during a period of weakening demand.

- The distribution warehouse recorded a 12-day restocking delay.

- Vendor inconsistencies were identified as a primary contributor to replenishment risk.

- The Midwest sales gap is mainly associated with distribution lag rather than demand conditions alone.

- Current visibility into supplier lead time, fill rate, inventory, and escalation thresholds needs strengthening.

## Slide 5 — Data Findings: Product and Category Trends

- Apparel—especially Running Shoes—showed a steady three-month decline in units sold and gross revenue.

- The decline was consistent across the Northeast and Midwest.

- Apparel had been underrepresented in recent campaigns, which were concentrated on Electronics.

- Running Shoes remain a high-margin product and therefore a priority for recovery.

- For Electronics, competitor Q4 bundles and limited-time rebates help explain the observed dip.

## Slide 6 — Data Findings: Regional Performance

- Northeast: Lower foot traffic and higher return rates, particularly in Q4.

- Midwest: Distribution lag is the principal issue affecting availability and sales.

- Regional performance should be decomposed by channel to separate pricing, traffic, returns, and supply effects.

- Pricing and region-specific campaigns require further assessment before scaling corrective measures.

## Slide 7 — Root-Cause View

- Supply: Vendor inconsistency, long replenishment lead time, backorders, and warehouse delay.

- Demand: Possible seasonality and uneven regional foot traffic.

- Marketing: Apparel underexposure and stronger competitor offers in Electronics.

- Customer behavior: Elevated Northeast return rates.

- Management information: Need for shared KPIs, channel-level baselines, and updated forecast assumptions.

## Slide 8 — Recommended Supply Chain Actions

- Complete the root-cause review of the 12-day warehouse delay.

- Implement dual-supplier sourcing before the next replenishment cycle.

- Monitor supplier lead time and fill rate weekly.

- Define escalation thresholds, backup allocation rules, and replenishment controls.

- Measure improvement through shorter restocking lead time, fewer backorders, and higher in-stock rate.

## Slide 9 — Recommended Commercial and Regional Actions

- Launch a social-first Running Shoes pilot using short-form video and influencer partnerships.

- Define target audience, budget, channels, and campaign reporting before launch.

- Develop an improved Electronics promotional calendar informed by competitor bundle and rebate patterns.

- Validate Northeast traffic and return drivers, including pricing and regional campaign options.

- Quantify the Midwest distribution lag and reflect it in regional action planning.

## Slide 10 — Action Plan, Owners, and Timing

| Workstream | Owner | Deliverable | Timing |
| --- | --- | --- | --- |
| Stock resilience | Alex Turner | Root-cause review, dual sourcing, supplier monitoring | Before next replenishment cycle |
| Regional performance | Emily Davis | Regional and channel-level recommendations | Next forecast cycle |
| Apparel marketing | James Lee | Running Shoes social campaign pilot | Early February 2025 |
| Competitive promotions | John Smith | Electronics timing and offer recommendations | Next forecast cycle |
| Governance | Sarah Thompson | Biweekly sync, progress report, forecast integration | Immediate and ongoing |

## Slide 11 — KPIs and Success Measures

- Supply: Restocking lead time, supplier fill rate, backorders, and in-stock rate.

- Sales: Running Shoes units sold and gross revenue by region and channel.

- Marketing: Reach, engagement, conversion, and revenue uplift from the pilot.

- Regional: Foot traffic, return rate, pricing response, and distribution lag.

- Execution: Action completion, risks, blockers, decisions, and forecast updates.

## Slide 12 — Risks, Mitigations, and Decisions Needed

- Campaign does not convert: Run a limited pilot and adjust audience, offer, or creative before scaling.

- Dual sourcing does not resolve delays: Use weekly supplier monitoring, escalation thresholds, and backup allocation rules.

- Regional findings remain inconclusive: Separate pricing, traffic, returns, and distribution effects using channel-level data.

- Cross-functional work becomes disconnected: Maintain one action register with owners, due dates, KPIs, decisions, and blockers.

- Leadership decisions: Confirm pilot budget, dual-sourcing approvals, KPI ownership, and revised forecast assumptions.

## Slide 13 — Next Steps and Governance Cadence

- Consolidate competitive, regional, and supply recommendations by late January.

- Activate dual-supplier controls and launch the Apparel pilot in early February.

- Update demand, campaign, regional, and supply assumptions in the February forecasting cycle.

- Hold biweekly cross-functional reviews covering progress, KPI movement, blockers, risks, and decisions.

- Provide consolidated progress and escalation reporting to the VP of Sales.