# Sales Trends Improvement Project Action Plan

Project period: January–February 2025
Project lead: Sarah Thompson
Purpose: Reverse declining sales, improve product availability, and address regional performance gaps through coordinated sales, marketing, finance, and operations actions.

## 1. Objectives and Success Measures

- Restore sales momentum for Running Shoes in the Northeast and Midwest.

- Reduce stock disruption by addressing vendor and distribution delays.

- Improve campaign visibility for Apparel while strengthening promotional timing for Electronics.

- Incorporate revised regional, marketing, and supply assumptions into the next forecasting cycle.

- Track progress through biweekly reviews and a consolidated progress report.

## 2. Action Roadmap

| Workstream | Owner | Key Actions and Deliverables | Target | Success Measure |
| --- | --- | --- | --- | --- |
| Competitive promotions | John Smith | Complete promotion analysis for Electronics; document Q4 bundle and rebate patterns; recommend next-quarter timing and offer concepts. | Analysis completed; recommendations ready for next forecast cycle | Approved promotional calendar and offer recommendations |
| Apparel marketing | James Lee | Finalize social-first Running Shoes campaign; prepare short-form video and influencer pilot; define audience, budget, channels, and reporting. | Pilot launch in early February 2025 | Campaign reach, engagement, conversion, and Running Shoes revenue uplift |
| Stock resilience | Alex Turner | Complete root-cause review of the 12-day warehouse delay; implement dual-supplier sourcing; define vendor and replenishment monitoring. | Controls active before the next replenishment cycle | Shorter restocking lead time, fewer backorders, improved in-stock rate |
| Regional performance | Emily Davis | Validate Northeast foot-traffic and return-rate drivers; assess pricing and regional campaign options; quantify Midwest distribution lag. | Recommendations ready for next forecast cycle | Regional action recommendations with channel-level baseline metrics |
| Governance and reporting | Sarah Thompson | Issue progress report to the VP of Sales; establish biweekly cross-functional sync; integrate revised assumptions into next month’s forecast. | Immediate setup and monthly forecast inclusion | Regular status reporting, decisions logged, forecast updated |

## 3. Milestones

- January 20: Follow-up review completed; initial findings and mitigation actions confirmed.

- Late January: Competitive, regional, and stock recommendations consolidated.

- Early February: Apparel campaign pilot launched and dual-supplier controls operational.

- February forecasting cycle: Revised commercial and operational assumptions incorporated.

- Biweekly thereafter: Progress, risks, KPI movement, and decisions reviewed.

## 4. Dependencies

- Timely access to sales, channel, return, inventory, and supplier performance data.

- Agreement between Sales, Marketing, Finance, and Operations on KPIs and forecast assumptions.

- Marketing budget and creative capacity for the campaign pilot.

- Supplier readiness and commercial approval for dual-sourcing arrangements.

## 5. Key Risks and Mitigations

| Risk | Mitigation |
| --- | --- |
| Campaign engagement does not translate into sales. | Use a limited pilot, track conversion, and adjust audience, offer, or creative before scaling. |
| Dual sourcing does not resolve replenishment delays. | Monitor supplier lead time and fill rate weekly; define escalation thresholds and backup allocation rules. |
| Regional findings remain inconclusive. | Separate pricing, traffic, returns, and distribution effects using channel-level analysis. |
| Cross-functional actions become disconnected. | Maintain one action register with owners, due dates, KPIs, decisions, and blockers. |

## 6. Governance and Reporting Cadence

- Biweekly project sync: Review action status, KPI changes, blockers, and decisions.

- Owner updates: Submit concise progress and risk updates before each sync.

- Monthly forecast review: Refresh demand, campaign, regional, and supply assumptions.

- Executive reporting: Sarah Thompson consolidates progress and escalations for the VP of Sales.