# Supply Chain Issues Review – Action Plan

This action plan addresses the quality, traceability, compliance, delivery, and production risks associated with BIND567, COMP042, and COMP043.

## General Strategies

- Protect production continuity: Prioritize actions according to operational impact, regulatory exposure, and material criticality.

- Strengthen supplier governance: Set clear corrective-action expectations, deadlines, escalation paths, and consequences for non-performance.

- Use parallel sourcing: Develop qualified alternatives for all three components to reduce dependency on underperforming suppliers.

- Improve controls: Tighten incoming quality checks, traceability verification, GMP oversight, and shipment documentation review.

- Coordinate cross-functionally: Maintain a task force covering Quality, Procurement, Supply Chain, Operations, and Regulatory or Compliance functions.

- Base decisions on evidence: Track rejection rates, stock levels, shipment delays, documentation gaps, audit findings, and corrective-action closure.

## Immediate Actions

| Action | Owner | Target | Expected Outcome |
| --- | --- | --- | --- |
| Validate current BIND567 batches by performing molecular consistency tests and submitting the findings. | David Okoro | 8 December 2024 | Unsafe or nonconforming material is prevented from entering production. |
| Issue a formal escalation to the BIND567 supplier requesting root-cause analysis, containment, corrective actions, and a firm recovery schedule. | Ravi Patel / Procurement | Within 24 hours | Supplier accountability and a documented recovery plan are established. |
| Reconcile COMP042 manifests, lot numbers, certificates, and origin records for open and recent shipments. | Maria Sanchez / Supply Chain | Within 48 hours | Traceability gaps are identified and affected shipments are held or cleared. |
| Launch an urgent GMP and cleanroom-practice review for COMP043 and request immediate supplier containment. | Maria Sanchez / Quality | Within 48 hours | Contamination and compliance risks are contained. |
| Assess inventory, production schedules, and stockout exposure for all three components; identify critical production windows. | Eleanor Wright / Operations | Within 24 hours | Near-term production risks and required prioritization are visible. |
| Form the cross-functional task force and establish a shared issue, risk, decision, and action tracker. | Sarah Nakamura / Meeting Sponsor | Immediately | Responsibilities, deadlines, and escalation decisions are centrally managed. |

## Short-Term Actions (1–3 Weeks)

| Action | Owner | Target | Expected Outcome |
| --- | --- | --- | --- |
| Source an alternative supplier for BIND567, expedite onboarding, and validate supplier reliability. | Ravi Patel | 12 December 2024 | An alternative BIND567 supplier is onboarded on an expedited basis and its reliability is validated. |
| Audit PrimeLogistics for COMP042, document traceability gaps, and propose corrective actions. | Ravi Patel | 10 December 2024 | Traceability gaps and corrective actions are documented for the logistics process. |
| Coordinate GMP remediation for COMP043, establish a timeline with the supplier, and track improvements. | Maria Sanchez and Quality | 15 December 2024 | A supplier remediation schedule is agreed and improvement progress is tracked. |
| Initiate parallel sourcing for COMP043 by identifying and vetting alternative suppliers. | Ravi Patel | 20 December 2024 | Qualified backup options for COMP043 are identified for further onboarding. |
| Build a component-level contingency plan covering safety stock, allocation rules, substitute materials, and production sequencing. | Eleanor Wright | Week 2 | Operational disruption is minimized if recovery is delayed. |
| Document COMP042 traceability gaps and prepare a report for FDA review. | Maria Sanchez | 11 December 2024 | Compliance evidence and decision history are complete. |

## Ongoing Actions

- Weekly governance: Review risks, blocked actions, supplier commitments, inventory coverage, and production impact; escalate overdue items.

- Supplier scorecards: Monitor quality rejection rate, on-time delivery, documentation accuracy, GMP compliance, responsiveness, and corrective-action closure.

- Quality and compliance monitoring: Trend BIND567 test results, COMP042 traceability exceptions, and COMP043 audit or contamination findings.

- Inventory resilience: Reassess safety-stock levels and sourcing concentration using demand, lead-time, and disruption data.

- Alternative supplier qualification: Progress technical, quality, commercial, and compliance assessments until approved backups are operational.

- Lessons learned: Update procurement requirements, receiving controls, contracts, escalation procedures, and business-continuity plans based on findings.

- Closure criteria: Close each issue only after effectiveness checks confirm sustained quality, full traceability, acceptable compliance, dependable delivery, and manageable production risk.