Microsoft Copilot Task Assignments in Planner:

Task 1: Validate Current Batches for BIND567

- Owner: David Okoro

- Due Date: December 8, 2024

- Notes: Perform molecular consistency tests and submit findings.

Task 2: Source Alternative Supplier for BIND567

- Owner: Ravi Patel

- Due Date: December 12, 2024

- Notes: Expedite supplier onboarding and validate reliability.

Task 3: Audit PrimeLogistics for COMP042

- Owner: Ravi Patel

- Due Date: December 10, 2024

- Notes: Document traceability gaps and propose corrective actions.

Task 4: Document Traceability Gaps for COMP042

- Owner: Maria Sanchez

- Due Date: December 11, 2024

- Notes: Prepare a report for FDA review.

Task 5: Coordinate GMP Remediation for COMP043

- Owner: Maria Sanchez

- Due Date: December 15, 2024

- Notes: Establish timeline with supplier and track improvements.

Task 6: Initiate Parallel Sourcing for COMP043

- Owner: Ravi Patel

- Due Date: December 20, 2024

- Notes: Identify and vet alternative suppliers.